lnkmx 6-Week App Roadmap

Planning window: March 9, 2026 - April 19, 2026

Goal: launch the Q2 monetization pivot without breaking the strengths already present in the repo - the page builder, Dashboard V2, Business Zones CRM, invoicing/documents, analytics, SEO/SSR, PWA shell, and Capacitor mobile wrappers.

Repo basis used for this roadmap: README, PLATFORM_SNAPSHOT, product roadmap/tech debt docs, dependency-cruiser rules, tier hooks and monetization screens, fintech service, Zone screens, and manifest/service worker behavior.

Current Repo Baseline

- The repo already ships a broad surface area: 28+ block page builder, public pages, Dashboard V2, Business Zones (deals, contacts, tasks, invoices, documents, products, events, automations), SEO/SSR, i18n, PWA assets, and Capacitor shells.

- Several CRM depth features are already present in code, including multi-pipeline support, custom contact/deal fields, Excel exports, invoice PDF export, and a Zone command palette/global search.

- The clearest near-term gap is monetization alignment: docs call for Identity/Starter/Pro with 7% and 1% fee handling, while current hooks and billing UI still model free/pro/business and the fintech service still carries a 5% default take-rate.

- Billing/account UX is unfinished in places: Account Settings still contains TODO placeholders for billing history and password change, and the payment service is still described as a skeleton.

- PWA/offline support is basic today: the service worker caches a small static set and images, but not the deeper read-only CRM workflow described in Q2 plans.

- Zone analytics exists, but it is still a summary dashboard rather than a full operating/reporting surface for finance, funnel trends, and team throughput.

Architecture Constraints

- Protect Supabase RLS and zone isolation on every billing, reporting, and CRM change.

- Respect dependency-cruiser boundaries between core/shared code and UI/data layers.

- Keep bundle growth under control; the app already lazy-loads shell pieces and zone screens for performance.

- Treat Edge Function changes as security-sensitive because several public endpoints rely on internal auth checks instead of JWT verification.

- Keep quality gates green: typecheck, lint, unit tests, E2E flows, and dependency analysis.

Milestones

- Milestone 1 - End of Week 2: monetization foundation live across tier rules, payment flows, fee handling, and billing surfaces.

- Milestone 2 - End of Week 4: business-ready CRM polish with stronger reporting, accessible mobile UX, and fewer inconsistent workflows.

- Milestone 3 - End of Week 6: release-ready PWA/mobile reliability, launch checklist completion, and KPI tracking for Starter launch and Pro conversion.

Week-by-Week Plan

| Week | Focus / Weekly goal | Deliverables | Dependencies and risks |
| --- | --- | --- | --- |
| Week 1 Mar 9 - Mar 15 | Monetization model alignment | - Replace free/pro/business assumptions with Identity/Starter/Pro/Business rules in tier hooks, limits, pricing copy, and the Monetize screen. - Centralize fee constants and remove the legacy 5% take-rate fallback. - Define the event/data model for fee calculation, settlement, and billing history. | - Dependency: product sign-off on the plan matrix and upgrade thresholds. - Risk: gating bugs or revenue leakage if tier mapping stays inconsistent. |
| Week 2 Mar 16 - Mar 22 | Payment execution and account billing | - Implement the missing process-transaction-fee flow plus webhook/idempotency handling. - Finish the Robokassa order lifecycle and decide Kaspi scope (full automation vs staged rollout). - Replace the billing-history placeholder and wire password-change/support flow in account settings. - Expand fintech E2E coverage for purchase, webhook, and failed/retried payment cases. | - Dependency: provider credentials, webhook sandbox access, and fee/refund rules. - Risk: reconciliation drift and service-role/RLS mistakes in financial paths. |
| Week 3 Mar 23 - Mar 29 | Reporting and business visibility | - Expand ZoneAnalytics beyond summary cards into finance-ready reporting: funnel trends, invoice conversion, paid vs pending totals, and assignee/task throughput. - Validate and polish existing exports, search, pipelines, and custom fields in real operator workflows. - Add billing/plan metrics for Starter adoption and upgrade triggers. | - Dependency: seeded zone data and complete analytics events. - Risk: slow client-side queries or noisy metrics on larger zones. |
| Week 4 Mar 30 - Apr 5 | Mobile-first UX hardening | - Remove critical sub-12px text and undersized touch targets in dashboard/zone surfaces. - Standardize error handling and toast patterns across zone screens. - Add screen-level error boundaries and stronger empty/loading states around zone workspaces. - Run responsive QA on Dashboard V2, zones, invoices, bookings, and account settings. | - Dependency: design QA bandwidth and device coverage. - Risk: layout regressions across small-screen variants if changes are too broad at once. |
| Week 5 Apr 6 - Apr 12 | PWA V2 and offline read mode | - Extend the service worker beyond minimal asset/image caching. - Ship read-only offline access for high-value zone data: contacts, tasks, and invoices, with clear freshness indicators. - Define a deferred-write strategy; if full offline mutations are too risky, explicitly queue or disable them. - Validate install/update behavior across web PWA and Capacitor shells. | - Dependency: cache invalidation policy, storage strategy, and a product decision on offline writes. - Risk: stale data, chunk mismatch, and sync conflicts if scope is too ambitious. |
| Week 6 Apr 13 - Apr 19 | Release hardening and launch | - Run regression passes on auth, page creation, CRM workflow, fintech flow, zone upgrade, and visual smoke paths. - Complete the launch checklist: pricing/legal copy, support runbooks, rollback plan, and monitoring alerts. - Hold a go/no-go review with open bug burn-down and KPI dashboards for Starter to Pro conversion. | - Dependency: stable staging environment and owner availability for sign-off. - Risk: carryover from payment or offline work can delay launch if it is not contained earlier. |

Explicit Dependencies

- Supabase migrations, RPCs, and Edge Function deployment for tiering, fees, reporting, and billing history.

- Payment provider credentials and webhook sandbox coverage for Robokassa; Kaspi API readiness if included in scope.

- Product/legal sign-off on plan naming, commission rules, billing copy, and refund handling.

- A QA data set that covers zones, invoices, bookings, multi-user workflows, and premium plan transitions.

- Translation updates for pricing, billing, and account settings across core locales.

Explicit Risks

- Monetization mismatch between docs and code can expose premium features incorrectly or lose fee revenue.

- Multi-tenant and RLS regressions are high impact because zones, invoices, and analytics all cross protected data boundaries.

- Webhook/payment flows are retry-heavy; idempotency and settlement visibility should be treated as launch blockers.

- Mobile-first cleanup can sprawl if every screen is touched at once; prioritize zones, billing, and onboarding paths first.

- Offline scope expands quickly; keep Week 5 read-only unless conflict resolution is already designed.

Success Measures

- Starter tier is visible and selectable end-to-end in UI and backend.

- Fee events reconcile cleanly with orders, wallet/ledger entries, and billing history.

- Zone analytics works as an operator dashboard, not only as a summary card surface.

- Core PWA install, update, and offline read flows are validated.

- Quality gates stay green: typecheck, lint, tests, E2E critical paths, and dependency analysis.